## Simple Gannt Chart
PMP Project Tracking Gantt Chart
Task ID | Description | Planned Duration (days) | Start | Planned End (Start + Planned Duration) | Predecessor | Successor | Milestone (Coloured Green) | Phase Milestone (Coloured Orange) | Wk1 |  |  |  |  | Wk2 |  |  |  |  | Wk3 |  |  |  |  | Wk4 |  |  |  |  | Wk5 |  |  |  |  | Wk6 |  |  |  |  | Wk7 |  |  |  |  | Wk8 |  |  |  |  | Wk9 |  |  |  |  | Wk10 |  |  |  |  | Wk11 |  |  |  |  | Wk12 |  |  |  |  | Wk12 |  |  |  |  | Wk13 |  |  |  |  | Wk14 |  |  |  |  | Wk15 |  |  |  |  | Wk16 |  |  |  |  | Wk17 |  |  |  |  | Wk18 |  |  |  |  | Wk19 |  |  |  |  | Wk20 |  |  |  |  | Wk21 |  |  |  |  | Wk22 |  |  |  |  | Wk23 |  |  |  |  | Wk24 |  |  |  |  | Wk25 |  |  |  |  | Wk26 |  |  |  |  | Wk27 |  |  |  |  | Wk28 |  |  |  |  | Wk29 |  |  |  |  | Wk30 |  |  |  |  | Wk31 |  |  |  |  | Wk32 |  |  |  |  | Wk33 |  |  |  |  | Wk34 |  |  |  |  | Wk35 |  |  |  |  | Wk36 |  |  |  |  | Wk37 |  |  |  |  | Wk38 |  |  |  |  | Wk39 |  |  |  |  | Wk40 |  |  |  |  | Wk41 |  |  |  |  | Wk42 |  |  |  |  | Wk43 |  |  |  |  | Wk44 |  |  |  |  | Wk45 |  |  |  |  | Wk46 |  |  |  |  | Wk47 |  |  |  |  | Wk48 |  |  |  |  | Wk49 |  |  |  |  | Wk50 |  |  |  |  | Wk51 |  |  |  |  | Wk52 |  |  |  |  | Wk53 |  |  |  |  | Wk54 |  |  |  |  | Wk55 |  |  |  |  | Wk56 |  |  |  |  | Wk57
[9 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Clarify EMS deliverables with stakeholders | 1 | Thursday, May 01, 2025 | Thursday, May 01, 2025 | - | T2 | Scope and WBS formally documented and approved by project sponsor | bar: Wk1 Day 4
2 | Structure EMS deliverables into a Work Breakdown Structure (WBS) | 2 | Friday, May 02, 2025 | Monday, May 05, 2025 | T1 | T3 | bar: Wk1 Day 5 to Wk2 Day 1
3 | Document project assumptions and constraints | 1 | Tuesday, May 06, 2025 | Tuesday, May 06, 2025 | T2 | T4 | bar: Wk2 Day 2
4 | Define project success criteria | 1 | Wednesday, May 07, 2025 | Wednesday, May 07, 2025 | T3 | T5 | bar: Wk2 Day 3
5 | Identify stakeholders and their roles | 1 | Thursday, May 08, 2025 | Thursday, May 08, 2025 | T4 | T6 | Stakeholder register and engagement plan validated and signed off | bar: Wk2 Day 4
6 | Analyse and prioritise stakeholder influence and interests | 2 | Friday, May 09, 2025 | Monday, May 12, 2025 | T5 | T7 | bar: Wk2 Day 5 to Wk3 Day 1
7 | Develop stakeholder communication plan | 2 | Tuesday, May 13, 2025 | Wednesday, May 14, 2025 | T6 | T8 | bar: Wk3 Day 2 to Wk3 Day 3
8 | Compile initial EMS project charter | 2 | Thursday, May 15, 2025 | Friday, May 16, 2025 | T7 | T9 | Project charter endorsed by NEC board and PMP team | bar: Wk3 Day 4 to Wk3 Day 5
9 | Review EMS project charter (internal and NEC) | 3 | Monday, May 19, 2025 | Wednesday, May 21, 2025 | T8 | T10 | bar: Wk4 Day 1 to Wk4 Day 3
10 | Obtain approvals for EMS project charter | 3 | Thursday, May 22, 2025 | Monday, May 26, 2025 | T9 | T11 | bar: Wk4 Day 4 to Wk5 Day 1
11 | Document project team structure | 2 | Tuesday, May 20, 2025 | Wednesday, May 21, 2025 | T10 | T12 | Core project team roles allocated and onboarding completed | Project initiation phase completed, with scope, charter, stakeholder plans, and team formally established. | bar: Wk4 Day 2 to Wk4 Day 3
12 | Assign core project team members | 2 | Thursday, May 22, 2025 | Friday, May 23, 2025 | T11 | T13 | Project team operational and governance structure implemented | bar: Wk4 Day 4 to Wk4 Day 5
13 | Establish project governance framework | 2 | Monday, May 26, 2025 | Tuesday, May 27, 2025 | T12 | T14 | bar: Wk5 Day 1 to Wk5 Day 2
14 | Develop escalation procedures | 2 | Wednesday, May 28, 2025 | Thursday, May 29, 2025 | T13 | T15 | bar: Wk5 Day 3 to Wk5 Day 4
15 | Define decision-making hierarchy | 2 | Friday, May 30, 2025 | Monday, May 31, 2025 | T14 | T16 | bar: Wk5 Day 5 to Wk6 Day 1
16 | Develop stakeholder engagement plan | 2 | Tuesday, June 03, 2025 | Wednesday, June 11, 2025 | T15 | T17 | Feasibility report and engagement plan reviewed and endorsed by stakeholders | bar: Wk6 Day 2 to Wk6 Day 3
17 | Conduct project feasibility analysis (technical + financial) | 3 | Thursday, June 05, 2025 | Monday, June 09, 2025 | T16 | T18 | bar: Wk6 Day 4 to Wk7 Day 1
18 | Conduct risk assessment workshop | 3 | Tuesday, June 10, 2025 | Thursday, June 12, 2025 | T17 | T19 | Initial risk register approved and integrated into planning documentation | bar: Wk7 Day 2 to Wk7 Day 4
19 | Create preliminary risk register | 2 | Friday, June 13, 2025 | Monday, June 16, 2025 | T18 | T20 | bar: Wk7 Day 5 to Wk8 Day 1
20 | Define major project phases | 3 | Tuesday, June 17, 2025 | Thursday, June 19, 2025 | T19 | T21 | Project schedule, structure, and resource plan validated and agreed upon | bar: Wk8 Day 2 to Wk8 Day 4
21 | Set high-level estimated timelines | 3 | Friday, June 20, 2025 | Tuesday, June 24, 2025 | T20 | T22 | bar: Wk8 Day 5 to Wk9 Day 2
22 | Identify key internal dependencies | 2 | Wednesday, June 25, 2025 | Thursday, June 26, 2025 | T21 | T23 | bar: Wk9 Day 3 to Wk9 Day 4
23 | Identify key external dependencies | 2 | Friday, June 27, 2025 | Monday, June 30, 2025 | T22 | T24 | bar: Wk9 Day 5 to Wk10 Day 1
24 | Set up project team and allocate resources. | 3 | Tuesday, July 01, 2025 | Thursday, July 03, 2025 | T23 | T25 | bar: Wk10 Day 2 to Wk10 Day 4
25 | Develop project budget | 2 | Friday, June 27, 2025 | Monday, June 30, 2025 | T24 | T26 | High-level budget and CBS finalised and authorised | bar: Wk9 Day 5 to Wk10 Day 1
26 | Break down budget by phase | 2 | Tuesday, July 01, 2025 | Wednesday, July 02, 2025 | T25 | T27 | bar: Wk10 Day 2 to Wk10 Day 3
27 | Develop cost breakdown structure | 2 | Thursday, July 03, 2025 | Friday, July 04, 2025 | T26 | T28 | bar: Wk10 Day 4 to Wk10 Day 5
28 | Establish procurement requirements | 1 | Monday, July 07, 2025 | Monday, July 07, 2025 | T27 | T29 | Procurement plan approved and RFP process launched | bar: Wk11 Day 1
29 | Draft vendor selection criteria | 1 | Tuesday, July 08, 2025 | Tuesday, July 08, 2025 | T28 | T30 | bar: Wk11 Day 2
30 | Review vendor selection criteria with NEC procurement | 1 | Wednesday, July 09, 2025 | Wednesday, July 09, 2025 | T29 | T31 | bar: Wk11 Day 3
31 | Initiate vendor selection process | 1 | Thursday, July 10, 2025 | Thursday, July 10, 2025 | T30 | T32 | bar: Wk11 Day 4
32 | Shortlist vendors for EMS development | 1 | Friday, July 11, 2025 | Friday, July 11, 2025 | T31 | T33 | bar: Wk11 Day 5
33 | Develop communication strategy | 1 | Monday, July 14, 2025 | Monday, July 14, 2025 | T32 | T34 | Communication strategy rolled out across project team and stakeholders | bar: Wk12 Day 1
34 | Schedule stakeholder briefing sessions | 1 | Tuesday, July 15, 2025 | Tuesday, July 15, 2025 | T33 | T35 | bar: Wk12 Day 2
35 | Set up project collaboration tools (Teams, Slack, Email) | 1 | Wednesday, July 16, 2025 | Wednesday, July 16, 2025 | T34 | T36 | bar: Wk12 Day 3
36 | Conduct stakeholder interviews | 1 | Thursday, July 17, 2025 | Thursday, July 17, 2025 | T35 | T37 | Requirements document signed off by all relevant stakeholders | bar: Wk12 Day 4
37 | Create requirement gathering plan | 1 | Friday, July 18, 2025 | Friday, July 18, 2025 | T36 | T38 | bar: Wk12 Day 5
38 | Conduct workshops to gather functional and non-functional requirements | 1 | Monday, July 21, 2025 | Monday, July 21, 2025 | T37 | T39 | bar: Wk12 Day 1
39 | Document functional and non-functional requirements | 1 | Tuesday, July 22, 2025 | Tuesday, July 22, 2025 | T38 | T40 | bar: Wk12 Day 2
40 | Validate and obtain stakeholder approval for all documented requirements | 1 | Wednesday, July 23, 2025 | Wednesday, July 23, 2025 | T39 | T41 | bar: Wk12 Day 3
41 | Categorise approved requirements using MoSCoW | 1 | Thursday, July 24, 2025 | Thursday, July 24, 2025 | T40 | T42 | bar: Wk12 Day 4
42 | Define change request process | 1 | Friday, July 25, 2025 | Friday, July 25, 2025 | T41 | T43 | Change management and document control processes established | bar: Wk12 Day 5
43 | Set up document management system | 1 | Monday, July 28, 2025 | Monday, July 28, 2025 | T42 | T44 | bar: Wk13 Day 1
44 | Prepare high-level project schedule | 1 | Tuesday, July 29, 2025 | Tuesday, July 29, 2025 | T43 | T45 | Project timeline and quality gates incorporated into master schedule | bar: Wk13 Day 2
45 | Identify critical path activities | 1 | Wednesday, July 30, 2025 | Wednesday, July 30, 2025 | T44 | T46 | bar: Wk13 Day 3
46 | Define key project milestones | 1 | Thursday, July 31, 2025 | Thursday, July 31, 2025 | T45 | T47 | bar: Wk13 Day 4
47 | Establish quality management plan | 1 | Friday, August 01, 2025 | Friday, August 01, 2025 | T46 | T48 | Approved plans integrated into overall project plan and risk framework | bar: Wk13 Day 5
48 | Develop health, safety, and compliance plan | 1 | Monday, August 04, 2025 | Monday, August 04, 2025 | T47 | T49 | bar: Wk14 Day 1
49 | Review and approve plans | 1 | Tuesday, August 05, 2025 | Tuesday, August 05, 2025 | T48 | T50 | bar: Wk14 Day 2
50 | Create risk management plan | 1 | Wednesday, August 06, 2025 | Wednesday, August 06, 2025 | T49 | T51 | bar: Wk14 Day 3
51 | Develop risk mitigation strategies | 1 | Thursday, August 07, 2025 | Thursday, August 07, 2025 | T50 | T52 | bar: Wk14 Day 4
52 | Conduct project kick-off meeting | 1 | Friday, August 08, 2025 | Friday, August 08, 2025 | T51 | T53 | Kick-off meeting completed, and project artefacts distributed | bar: Wk14 Day 5
53 | Distribute approved project documents to stakeholders | 1 | Monday, August 11, 2025 | Monday, August 11, 2025 | T52 | T54 |  | Planning phase concluded (Governance, schedule, budget, and requirements baselined for execution) | bar: Wk15 Day 1
54 | Create high-level system design | 1 | Tuesday, August 12, 2025 | Tuesday, August 12, 2025 | T53 | T55 | System design documentation signed off by stakeholders and approved for development | bar: Wk15 Day 2
55 | Develop EMS system architecture | 1 | Wednesday, August 13, 2025 | Wednesday, August 13, 2025 | T54 | T56 | bar: Wk15 Day 3
56 | Develop data flow diagrams | 1 | Thursday, August 14, 2025 | Thursday, August 14, 2025 | T55 | T57 | bar: Wk15 Day 4
57 | Develop user interface wireframes | 1 | Friday, August 15, 2025 | Friday, August 15, 2025 | T56 | T58 | bar: Wk15 Day 5
58 | Conduct design review sessions | 1 | Monday, August 18, 2025 | Monday, August 18, 2025 | T57 | T59 | bar: Wk16 Day 1
59 | Finalize system design documents | 1 | Tuesday, August 19, 2025 | Tuesday, August 19, 2025 | T58 | T60 | bar: Wk16 Day 2
60 | Conduct design sign-off meeting | 2 | Wednesday, August 20, 2025 | Thursday, August 21, 2025 | T59 | T61 | bar: Wk16 Day 3 to Wk16 Day 4
61 | Set up Agile development team | 2 | Friday, August 22, 2025 | Monday, August 25, 2025 | T60 | T62 | Agile team assembled, backlog ready, CI pipeline and dev environment established | bar: Wk16 Day 5 to Wk17 Day 1
62 | Prepare product backlog | 1 | Tuesday, August 26, 2025 | Tuesday, August 26, 2025 | T61 | T63 | bar: Wk17 Day 2
63 | Develop sprint schedule and milestones | 2 | Wednesday, August 27, 2025 | Thursday, August 28, 2025 | T62 | T64 | bar: Wk17 Day 3 to Wk17 Day 4
64 | Conduct sprint planning meeting | 2 | Friday, August 29, 2025 | Monday, September 01, 2025 | T63 | T65 | bar: Wk17 Day 5 to Wk18 Day 1
65 | Establish Continuous Integration (CI) pipeline | 1 | Tuesday, September 02, 2025 | Tuesday, September 02, 2025 | T64 | T66 | bar: Wk18 Day 2
66 | Set up development environment | 2 | Wednesday, September 03, 2025 | Thursday, September 04, 2025 | T65 | T67 | bar: Wk18 Day 3 to Wk18 Day 4
67 | Develop ticketing and registration module | 4 | Friday, September 05, 2025 | Wednesday, September 10, 2025 | T66 | T68 | All core modules developed and unit tested, ready for integration | bar: Wk18 Day 5 to Wk19 Day 3
68 | Conduct unit testing for ticketing module | 2 | Thursday, September 11, 2025 | Friday, September 12, 2025 | T67 | T69 | bar: Wk19 Day 4 to Wk19 Day 5
69 | Develop artist management module | 4 | Monday, September 15, 2025 | Thursday, September 18, 2025 | T68 | T70 | bar: Wk20 Day 1 to Wk20 Day 4
70 | Conduct unit testing for artist module | 2 | Friday, September 19, 2025 | Monday, September 22, 2025 | T69 | T71 | bar: Wk20 Day 5 to Wk21 Day 1
71 | Develop vendor management module | 4 | Tuesday, September 23, 2025 | Friday, September 26, 2025 | T70 | T72 | bar: Wk21 Day 2 to Wk21 Day 5
72 | Conduct unit testing for vendor module | 2 | Monday, September 29, 2025 | Tuesday, September 30, 2025 | T71 | T73 | bar: Wk22 Day 1 to Wk22 Day 2
73 | Develop sponsor management module | 4 | Wednesday, October 01, 2025 | Monday, October 06, 2025 | T72 | T74 | bar: Wk22 Day 3 to Wk23 Day 1
74 | Conduct unit testing for sponsor module | 2 | Tuesday, October 07, 2025 | Wednesday, October 08, 2025 | T73 | T75 | bar: Wk23 Day 2 to Wk23 Day 3
75 | Develop event scheduling module | 4 | Thursday, October 09, 2025 | Tuesday, October 14, 2025 | T74 | T76 | bar: Wk23 Day 4 to Wk24 Day 2
76 | Conduct unit testing for scheduling module | 2 | Wednesday, October 15, 2025 | Thursday, October 16, 2025 | T75 | T77 | bar: Wk24 Day 3 to Wk24 Day 4
77 | Develop budget tracking module | 4 | Friday, October 17, 2025 | Wednesday, October 22, 2025 | T76 | T78 | bar: Wk24 Day 5 to Wk25 Day 3
78 | Conduct unit testing for budget module | 2 | Thursday, October 23, 2025 | Friday, October 24, 2025 | T77 | T79 | bar: Wk25 Day 4 to Wk25 Day 5
79 | Develop role-based access control | 2 | Monday, October 27, 2025 | Tuesday, October 28, 2025 | T78 | T80 | bar: Wk26 Day 1 to Wk26 Day 2
80 | Conduct unit testing for access control | 2 | Wednesday, October 29, 2025 | Thursday, October 30, 2025 | T79 | T81 | bar: Wk26 Day 3 to Wk26 Day 4
81 | Develop analytics dashboard | 3 | Friday, October 31, 2025 | Tuesday, November 04, 2025 | T80 | T82 | All modules integrated with no issues | bar: Wk26 Day 5 to Wk27 Day 2
82 | Conduct unit testing for analytics module | 2 | Wednesday, November 05, 2025 | Thursday, November 06, 2025 | T81 | T83 | bar: Wk27 Day 3 to Wk27 Day 4
83 | Integrate modules into single EMS platform | 2 | Friday, November 07, 2025 | Monday, November 10, 2025 | T82 | T84 | bar: Wk27 Day 5 to Wk28 Day 1
84 | Develop banned patrons list database | 1 | Tuesday, November 11, 2025 | Tuesday, November 11, 2025 | T83 | T85 | bar: Wk28 Day 2
85 | Develop supplier compliance checklist (e.g., WWCC, food permits) | 2 | Wednesday, November 12, 2025 | Thursday, November 13, 2025 | T84 | T86 | bar: Wk28 Day 3 to Wk28 Day 4
86 | Create automated financial reconciliation report templates | 2 | Friday, November 14, 2025 | Monday, November 17, 2025 | T85 | T87 | bar: Wk28 Day 5 to Wk29 Day 1
87 | Develop VIP guest registration and tracking system | 1 | Tuesday, November 18, 2025 | Tuesday, November 18, 2025 | T86 | T88 | bar: Wk29 Day 2
88 | Implement event risk scenario planning system | 2 | Wednesday, November 19, 2025 | Thursday, November 20, 2025 | T87 | T89 | bar: Wk29 Day 3 to Wk29 Day 4
89 | Configure EMS for mobile device usage policy | 3 | Friday, November 21, 2025 | Tuesday, November 25, 2025 | T88 | T90 | bar: Wk29 Day 5 to Wk30 Day 2
90 | Integrate mobile restriction alerts to security staff | 2 | Wednesday, November 26, 2025 | Thursday, November 27, 2025 | T89 | T91 | bar: Wk30 Day 3 to Wk30 Day 4
91 | Develop emergency services digital access interface | 5 | Friday, November 28, 2025 | Thursday, December 04, 2025 | T90 | T92 | bar: Wk30 Day 5 to Wk31 Day 4
92 | Conduct system integration testing | 6 | Friday, December 05, 2025 | Friday, December 12, 2025 | T91 | T93 | Integration and sprint cycles completed, platform stabilised for UAT | bar: Wk31 Day 5 to Wk32 Day 5
93 | Conduct sprint review meetings | 2 | Monday, December 15, 2025 | Tuesday, December 16, 2025 | T92 | T94 | bar: Wk33 Day 1 to Wk33 Day 2
94 | Conduct sprint retrospectives | 1 | Wednesday, December 17, 2025 | Wednesday, December 17, 2025 | T93 | T95 | bar: Wk33 Day 3
95 | Update product backlog after each sprint | 1 | Thursday, December 18, 2025 | Thursday, December 18, 2025 | T94 | T96 | bar: Wk33 Day 4
96 | Prepare UAT environment | 4 | Friday, December 19, 2025 | Wednesday, December 24, 2025 | T95 | T97 | UAT approved, system accepted by NEC for deployment | bar: Wk33 Day 5 to Wk34 Day 3
97 | Conduct User Acceptance Testing (UAT) & Fixes | 6 | Thursday, December 25, 2025 | Thursday, January 01, 2026 | T96 | T98 | bar: Wk34 Day 4 to Wk35 Day 4
98 | Obtain UAT sign-off from NEC | 1 | Friday, January 02, 2026 | Friday, January 02, 2026 | T97 | T99 |  | Design & development phase concluded (EMS fully developed, tested, integrated, and signed off for infrastructure implementation) | bar: Wk35 Day 5
99 | Conduct initial site survey | 2 | Monday, January 05, 2026 | Tuesday, January 06, 2026 | T98 | T100 | Infrastructure Setup Plan, Configured Servers and Hosting Environment Ready. | bar: Wk36 Day 1 to Wk36 Day 2
100 | Finalize infrastructure requirements | 1 | Wednesday, January 07, 2026 | Wednesday, January 07, 2026 | T99 | T101 | bar: Wk36 Day 3
101 | Procure servers and hosting services | 3 | Thursday, January 08, 2026 | Monday, January 12, 2026 | T100 | T102 | bar: Wk36 Day 4 to Wk37 Day 1
102 | Install infrastructure hardware | 4 | Tuesday, January 13, 2026 | Friday, January 16, 2026 | T101 | T103 | bar: Wk37 Day 2 to Wk37 Day 5
103 | Set up EMS hosting environment | 3 | Monday, January 19, 2026 | Wednesday, January 21, 2026 | T102 | T104 | bar: Wk38 Day 1 to Wk38 Day 3
104 | Configure security protocols | 3 | Thursday, January 22, 2026 | Monday, January 26, 2026 | T103 | T105 | Security Protocols for EMS Configured | bar: Wk38 Day 4 to Wk39 Day 1
105 | Conduct penetration testing | 3 | Tuesday, January 27, 2026 | Thursday, January 29, 2026 | T104 | T106 | bar: Wk39 Day 2 to Wk39 Day 4
106 | Implement data encryption | 2 | Friday, January 30, 2026 | Monday, February 02, 2026 | T105 | T107 | bar: Wk39 Day 5 to Wk40 Day 1
107 | Establish data backup procedures | 2 | Tuesday, February 03, 2026 | Wednesday, February 04, 2026 | T106 | T108 | bar: Wk40 Day 2 to Wk40 Day 3
108 | Digitally map venue layout for emergency response teams | 3 | Thursday, February 05, 2026 | Monday, February 09, 2026 | T107 | T109 | CCTV and Venue Mapping Operational | bar: Wk40 Day 4 to Wk41 Day 1
109 | Integrate CCTV modules | 4 | Tuesday, February 10, 2026 | Friday, February 13, 2026 | T108 | T110 | bar: Wk41 Day 2 to Wk41 Day 5
110 | Develop a disaster recovery plan | 5 | Monday, February 16, 2026 | Friday, February 20, 2026 | T109 | T111 | Disaster recovery plan approved, Backup Process Tested and Documented | bar: Wk42 Day 1 to Wk42 Day 5
111 | Develop an automated EMS data backup process | 2.5 | Monday, February 23, 2026 | Wednesday, February 25, 2026 | T110 | T112 | bar: Wk43 Day 1 to Wk43 Day 3
112 | Integrate emergency contact database | 3.5 | Thursday, February 26, 2026 | Tuesday, March 03, 2026 | T111 | T113 | bar: Wk43 Day 4 to Wk44 Day 2
113 | Conduct disaster recovery testing | 4 | Wednesday, March 04, 2026 | Monday, March 09, 2026 | T112 | T114 | bar: Wk44 Day 3 to Wk45 Day 1
114 | Prepare infrastructure deployment checklist | 2 | Tuesday, March 10, 2026 | Wednesday, March 11, 2026 | T113 | T115 | Compliance Certificates Obtained | bar: Wk45 Day 2 to Wk45 Day 3
115 | Obtain regulatory security certifications | 5 | Thursday, March 12, 2026 | Wednesday, March 18, 2026 | T114 | T116 |  | Infrastructure and security task completed | bar: Wk45 Day 4 to Wk46 Day 3
116 | Develop training materials | 2 | Thursday, March 19, 2026 | Friday, March 20, 2026 | T115 | T117 | Training Materials Approved, Staff/User Training Completed, Training Survey Responses Reviewed | bar: Wk46 Day 4 to Wk46 Day 5
117 | Schedule staff training sessions | 2 | Monday, March 23, 2026 | Tuesday, March 24, 2026 | T116 | T118 | bar: Wk47 Day 1 to Wk47 Day 2
118 | Conduct EMS training workshops | 3 | Wednesday, March 25, 2026 | Friday, March 27, 2026 | T117 | T119 | bar: Wk47 Day 3 to Wk47 Day 5
119 | Develop quick-start user guides | 3.2 | Monday, March 30, 2026 | Thursday, April 02, 2026 | T118 | T120 | bar: Wk48 Day 1 to Wk48 Day 4
120 | Conduct training sessions for users | 2.8 | Friday, April 03, 2026 | Tuesday, April 07, 2026 | T119 | T121 | bar: Wk48 Day 5 to Wk49 Day 2
121 | Conduct training feedback survey | 1.8 | Wednesday, April 08, 2026 | Thursday, April 09, 2026 | T120 | T122 | bar: Wk49 Day 3 to Wk49 Day 4
122 | Finalize Go-Live plan | 3.2 | Friday, April 10, 2026 | Wednesday, April 15, 2026 | T121 | T123 | Go-Live Strategy Finalized, System Readiness Confirmed, Go-Live Authorization Granted, Stakeholders notified. | bar: Wk49 Day 5 to Wk50 Day 3
123 | Conduct pre-Go-Live readiness check | 4.2 | Thursday, April 16, 2026 | Wednesday, April 22, 2026 | T122 | T124 | bar: Wk50 Day 4 to Wk51 Day 3
124 | Obtain Go-Live approval | 1.5 | Thursday, April 23, 2026 | Friday, April 24, 2026 | T123 | T125 | bar: Wk51 Day 4 to Wk51 Day 5
125 | Notify stakeholders of Go-Live date | 1 | Monday, April 27, 2026 | Monday, April 27, 2026 | T124 | T126 |  | Training and Golive task completed | bar: Wk52 Day 1
126 | Migrate EMS to production environment | 4 | Tuesday, April 28, 2026 | Friday, May 01, 2026 | T125 | T127 | EMS migrated to production and active. | bar: Wk52 Day 2 to Wk52 Day 5
127 | Activate EMS live services | 2 | Monday, May 04, 2026 | Tuesday, May 05, 2026 | T126 | T128 | bar: Wk53 Day 1 to Wk53 Day 2
128 | Monitor system performance post-deployment | 3.1 | Wednesday, May 06, 2026 | Monday, May 11, 2026 | T127 | T129 | EMS Go-Live Complete, First Week System Health Check Passed, Go-Live Support Hotline Operational. | bar: Wk53 Day 3 to Wk54 Day 1
129 | Deploy Go-Live support hotline | 2.2 | Tuesday, May 12, 2026 | Thursday, May 14, 2026 | T128 | T130 | bar: Wk54 Day 2 to Wk54 Day 4
130 | Address initial user issues | 3.2 | Friday, May 15, 2026 | Wednesday, May 20, 2026 | T129 | T131 | bar: Wk54 Day 5 to Wk55 Day 3
131 | Conduct post-implementation review | 2 | Thursday, May 21, 2026 | Friday, May 22, 2026 | T130 | T132 | Review Meeting Held and Documented, Major Issues Resolved Post-Go-Live, Operations Team Onboarded & Handover Done. | bar: Wk55 Day 4 to Wk55 Day 5
132 | Identify and fix issues post-implementation | 4.5 | Monday, May 25, 2026 | Friday, May 29, 2026 | T131 | T133 | bar: Wk56 Day 1 to Wk56 Day 5
133 | Transition to Maintenance & Support Team | 2.2 | Monday, June 01, 2026 | Wednesday, June 03, 2026 | T132 | T134 |  | Deployment and support task completed | bar: Wk57 Day 1 to Wk57 Day 3
134 | Archive Project Documentation | 1 | Thursday, June 04, 2026 | Thursday, June 04, 2026 | T133 | T135 | Formal Project Closure Signed | bar: Wk57 Day 4
135 | Conduct project closure and team recognition | 1 | Friday, June 05, 2026 | Friday, June 05, 2026 | T134 | - |  | Closure task completed | bar: Wk57 Day 5